## Project
Field | Value
Name | Card Disputes & Chargeback Automation
Code | CDA-1.0
Domain | Banking
Sub Domain | Cards & Disputes
Status | In Progress
Version | 1.0
Release | R2026.03
Owner | Saadaoui Abdessalem
Owner Role | Lead Functional Analyst
Business Owner | Head of Card Operations
Programme | Cards Modernisation
Summary | Automating the card dispute lifecycle from the cardholder raising a case to the chargeback being settled with the scheme.
Business Objective | Cut the cost per dispute by 45% and post every provisional credit within one working day.
Start Date | 2026-01-05
Target Date | 2026-06-30
Completion | 55
Regulatory Drivers | PSD2 Article 74; Scheme rules chapter 11
Tags | Cards, Disputes, Automation
Stack | Java, Spring Boot, PostgreSQL, Swagger, Postman, Docker

## Scope
Type | Item
In | Raising a dispute from a settled card transaction
In | Provisional credit and its reversal
In | Evidence upload while the case is under review
In | Chargeback submission to the scheme
Out | Merchant-side representment handling
Out | Fraud case management (separate programme)
Out | Cash and cheque disputes

## Stakeholders
ID | Name | Role | Email | Department | RACI
STK-001 | Head of Card Operations | Business Owner | card.ops@bank.example | Card Operations | Accountable
STK-002 | Saadaoui Abdessalem | Lead Functional Analyst | abdessalemsaa@gmail.com | Change Delivery | Responsible
STK-003 | Disputes Team Lead | Process Owner | disputes@bank.example | Card Operations | Consulted
STK-004 | Compliance Officer | Regulatory Assurance | compliance@bank.example | Compliance | Consulted
STK-005 | Head of Internal Audit | Assurance | audit@bank.example | Internal Audit | Informed

## Timeline
ID | Label | Date | Status | Description
MS-01 | Business case approved | 2026-01-05 | Completed | Cards steering committee approved the investment.
MS-02 | Requirements baselined | 2026-02-10 | Completed | Four requirements signed off with Operations and Compliance.
MS-03 | Functional specification approved | 2026-03-06 | In Progress | Field tables and error codes under review.
MS-04 | SIT and UAT | 2026-05-15 | Upcoming | Five test cases, two suites.
MS-05 | Go-live | 2026-06-30 | Upcoming | Pilot cohort first, then full rollout.

## Dependencies
ID | Name | Type | Owner | Status | Description
DEP-01 | Card scheme gateway | External Party | Integration Team | On Track | Chargeback submission and arbitration messages.
DEP-02 | Core banking ledger | Internal System | Core Banking | Resolved | Posting API for the provisional credit and its reversal.
DEP-03 | Document store | Vendor | Platform Team | At Risk | Evidence files; the 10 MB limit is not yet enforced server-side.

## Risks
ID | Description | Likelihood | Impact | Mitigation | Owner
R-01 | The provisional credit posts twice if the end-of-day run is replayed. | Medium | High | Idempotency key on the posting instruction, checked by SQL-002. | Saadaoui Abdessalem
R-02 | The attachment limit is enforced only in the app, not the API. | High | Medium | Move the check server-side before the March release; tracked by DEF-118. | Saadaoui Abdessalem
R-03 | Scheme rule changes in chapter 11 could shorten the dispute window. | Low | High | Window held in configuration, not code. | Compliance Officer

## Requirements
ID | Title | Business Need | Description | Priority | Status | Category | MoSCoW | Owner | Last Updated | Version | Rules | Tests | APIs | Documents
BR-001 | Raise a card dispute from a settled transaction | Disputes arrive by phone and are keyed by an agent, which costs 11 minutes per case and loses the evidence trail. | A cardholder selects a settled transaction from the last 120 days and raises a dispute against it, choosing a reason code. | Critical | Approved | Disputes | Must | Saadaoui Abdessalem | 2026-02-10 | 1.2 | RULE-001, RULE-002 | TC-001, TC-002 | API-001 | DOC-001
BR-002 | Credit the cardholder provisionally within one working day | Regulation requires the funds to be restored while the case is investigated; today it is manual and late. | Once a dispute is accepted, a provisional credit for the disputed amount is posted to the cardholder account. | Critical | Approved | Disputes | Must | Saadaoui Abdessalem | 2026-02-10 | 1.1 | RULE-003 | TC-003 | API-002 | DOC-001
BR-003 | Let the cardholder attach evidence to an open dispute | Cases stall waiting for a receipt that the cardholder already has on their phone. | Up to five files of 10 MB each may be attached to a dispute while its status is Under Review. | High | In Review | Disputes | Should | Saadaoui Abdessalem | 2026-02-14 | 0.4 | RULE-004 | TC-004 | API-003
BR-004 | Notify the cardholder at every change of dispute status | Two thirds of calls to the contact centre are cardholders asking where their case stands. | A notification is sent when a dispute moves to Under Review, Resolved or Rejected. | Medium | Draft | Notifications | Should | Saadaoui Abdessalem | 2026-02-18 | 0.2 |  | TC-005

## Acceptance Criteria
ID | Requirement | Given | When | Then
AC-001.1 | BR-001 | a settled card transaction dated within the last 120 days | the cardholder raises a dispute and selects a reason code | the dispute is created with the status Submitted and a reference is shown
AC-001.2 | BR-001 | a transaction older than 120 days | the cardholder opens it | the dispute action is unavailable and the reason is stated on screen
AC-001.3 | BR-001 | a transaction that already has an open dispute | the cardholder tries to dispute it again | the existing case is shown instead of a second one being created
AC-002.1 | BR-002 | a dispute accepted at 16:00 on a working day | the next end-of-day run completes | a provisional credit for the full disputed amount is posted
AC-002.2 | BR-002 | a dispute later rejected | the rejection is recorded | the provisional credit is reversed and the cardholder is told why
AC-003.1 | BR-003 | a dispute with the status Under Review and four files already attached | the cardholder attaches a fifth file of 8 MB | the file is accepted and the attach action is then disabled
AC-004.1 | BR-004 | a dispute that moves from Submitted to Under Review | the status change is saved | exactly one notification is sent to the cardholder

## Business Rules
ID | Description | Logic | Priority | Source | Status | Category | Owner | Effective From | Requirements
RULE-001 | A dispute may only be raised against a settled transaction. | IF transaction.status <> 'SETTLED' THEN reject WITH 'NOT_DISPUTABLE' | Critical | Scheme rules, chapter 11 | Approved | Eligibility | Saadaoui Abdessalem | 2026-01-01 | BR-001
RULE-002 | A transaction is disputable for 120 days after its settlement date. | IF today - transaction.settled_date > 120 THEN reject WITH 'WINDOW_CLOSED' | Critical | Scheme rules, chapter 11 | Approved | Eligibility | Saadaoui Abdessalem | 2026-01-01 | BR-001
RULE-003 | A provisional credit equals the disputed amount, never more. | credit.amount = dispute.amount AND credit.amount <= transaction.amount | Critical | Treasury policy 7.1 | Approved | Settlement | Saadaoui Abdessalem | 2026-01-01 | BR-002
RULE-004 | At most five evidence files, each at most 10 MB, per dispute. | IF files.count > 5 OR file.size > 10485760 THEN reject WITH 'ATTACHMENT_LIMIT' | Medium | Operations handbook 3.4 | In Review | Evidence | Saadaoui Abdessalem | 2026-03-01 | BR-003

## Actors
ID | Name | Type | Description | Responsibilities | Permissions | Systems | Channel
ACT-001 | Cardholder | Human | The retail customer whose card was charged. | Raises the dispute; supplies evidence; accepts the outcome | Read own transactions; create dispute; attach evidence | Mobile app; internet banking | Mobile
ACT-002 | Disputes agent | Human | Back-office analyst who investigates the case against the scheme rules. | Reviews evidence; decides the outcome; raises the chargeback | Read all disputes; change status; post adjustments | Disputes console; card management system | Back Office
ACT-003 | Card scheme | External | Visa or Mastercard, which arbitrates the chargeback. | Accepts the chargeback; rules on representment | Receive chargeback messages | Scheme gateway | File transfer
ACT-004 | Ledger | System | Posts the provisional credit and any later reversal. | Applies postings; guarantees a single posting per instruction | Write postings | Core banking | API

## Process Steps
Flow | Flow Name | Flow Description | Trigger | Outcome | SLA | Step ID | Step Name | Type | Lane | Description | Rules | Next
PF-001 | Raise and settle a card dispute | From the cardholder tapping Dispute to the case being closed. | The cardholder disputes a settled transaction | The case is Resolved or Rejected and the ledger agrees | Provisional credit within 1 working day; outcome within 45 days | S1 | Select the transaction | start | Cardholder | The cardholder opens a settled transaction in the app. |  | S2
PF-001 | [5 empty] | S2 | Check the dispute is allowed | decision | Disputes service | Status and the 120-day window are tested. | RULE-001, RULE-002 | S3, S9
PF-001 | [5 empty] | S3 | Capture the reason code | task | Cardholder | The cardholder picks a reason and confirms the amount. |  | S4
PF-001 | [5 empty] | S4 | Create the dispute | system | Disputes service | The case is created with the status Submitted. |  | S5
PF-001 | [5 empty] | S5 | Post the provisional credit | system | Ledger | The disputed amount is credited while the case is investigated. | RULE-003 | S6
PF-001 | [5 empty] | S6 | Investigate the case | task | Disputes agent | Evidence is read and the scheme rules applied. | RULE-004 | S7
PF-001 | [5 empty] | S7 | Raise the chargeback | task | Card scheme | The chargeback is sent to the scheme for arbitration. |  | S8
PF-001 | [5 empty] | S8 | Close the case | end | Disputes service | The case is Resolved; the provisional credit stands or is reversed.
PF-001 | [5 empty] | S9 | Refuse the dispute | end | Disputes service | The cardholder is told which condition failed.

## Spec Sections
ID | Title | Summary | Requirements | Business Logic
FS-001 | Raising a dispute | How a dispute is created from a settled transaction: what is checked, what is stored, and what the cardholder is told at each refusal. | BR-001 | 1. Read the transaction and confirm it is settled 2. Confirm the settlement date is within 120 days of today 3. Confirm no open dispute already exists for it 4. Store the dispute with the status Submitted and return its reference
FS-002 | Provisional credit | How the disputed amount is returned to the cardholder while the case is investigated, and how it is reversed if the dispute fails. | BR-002 | 1. On acceptance, queue a posting for the disputed amount 2. Post it in the next end-of-day run 3. On rejection, reverse the posting and notify the cardholder
FS-003 | Evidence handling | What a cardholder may attach to an open case, and what is refused. | BR-003 | 1. Accept files only while the case is Under Review 2. Refuse a sixth file, or any file over 10 MB 3. Store the file against the dispute, never against the transaction

## Spec Fields
Section | Name | Type | Length | Mandatory | Description | Example
FS-001 | transactionId | uuid | 36 | Yes | The settled transaction being disputed. | 9f2c1b7e-4a2d-4f9a-8b31-0c5e2a7d9f10
FS-001 | reasonCode | varchar | 10 | Yes | Why the cardholder disputes the charge, in scheme terms. | 13.1
FS-001 | amount | numeric | 15,2 | Yes | The disputed amount; may be less than the transaction, never more. | 84.50
FS-001 | description | varchar | 500 | No | The cardholder's own account of what happened. | Charged twice for one meal
FS-002 | postingId | uuid | 36 | Yes | The ledger posting that carries the provisional credit. | 3d81c0aa-71f4-4d2e-9c6b-6f0b2b1e77a2
FS-002 | valueDate | date | 10 | Yes | The date the credit takes effect on the account. | 2026-02-11
FS-003 | fileName | varchar | 255 | Yes | The name of the attached evidence file. | receipt-2026-02-08.pdf
FS-003 | sizeBytes | bigint | — | Yes | File size, checked against the 10 MB limit. | 2411008

## Spec Validations
Section | Field | Rule | Error Code | Severity
FS-001 | transactionId | Must reference a transaction whose status is SETTLED | NOT_DISPUTABLE | Blocking
FS-001 | transactionId | Settlement date must be within 120 days of today | WINDOW_CLOSED | Blocking
FS-001 | transactionId | No dispute may already be open against this transaction | ALREADY_DISPUTED | Blocking
FS-001 | amount | Must be greater than zero and at most the transaction amount | AMOUNT_INVALID | Blocking
FS-001 | reasonCode | Must be one of the scheme reason codes in force | REASON_UNKNOWN | Blocking
FS-002 | amount | The credit must equal the disputed amount exactly | CREDIT_MISMATCH | Blocking
FS-003 | sizeBytes | At most 10485760 bytes per file | ATTACHMENT_TOO_LARGE | Blocking
FS-003 | fileName | Extension should be pdf, png or jpg | ATTACHMENT_TYPE | Warning

## Spec Errors
Section | Code | HTTP Status | Message | Handling
FS-001 | NOT_DISPUTABLE | 422 | This transaction cannot be disputed yet. | Tell the cardholder to wait until the payment settles, and show the date.
FS-001 | WINDOW_CLOSED | 422 | The 120-day window for disputing this payment has passed. | Show the deadline that passed and offer the contact centre.
FS-001 | ALREADY_DISPUTED | 409 | There is already an open dispute for this payment. | Take the cardholder to the existing case rather than refusing.
FS-001 | AMOUNT_INVALID | 400 | The disputed amount is not valid. | Reset the field to the full transaction amount.
FS-002 | CREDIT_MISMATCH | 500 | The provisional credit does not match the disputed amount. | Hold the posting and raise an operations alert; never post a partial credit.
FS-003 | ATTACHMENT_LIMIT | 422 | You can attach up to five files. | Hide the attach action once five files exist, rather than failing on the sixth.
FS-003 | ATTACHMENT_TOO_LARGE | 413 | That file is larger than 10 MB. | Say the limit before the upload starts, not after it finishes.

## Spec Edge Cases
Section | ID | Scenario | Expected Behaviour
FS-001 | EC-001 | The transaction settles while the cardholder is on the screen | The Dispute action becomes available without a reload; no error is shown for the earlier state.
FS-001 | EC-002 | The dispute is submitted on day 120 at 23:59 local time | It is accepted; the window is counted in whole days against the settlement date, not in hours.
FS-001 | EC-003 | The cardholder taps Submit twice | One dispute is created; the second call returns the same reference.
FS-002 | EC-004 | The account is closed before the provisional credit posts | The credit is held and an operations task is raised; the case continues regardless.
FS-002 | EC-005 | The transaction is refunded by the merchant while the case is open | The provisional credit is reversed and the case is closed as Resolved, with one notification only.
FS-003 | EC-006 | The case moves to Resolved while a file is uploading | The upload completes and is stored, but no further file is accepted.

## Diagrams
ID | Title | Type | Description | Version | Author | Last Updated | Requirements | PlantUML
DGM-001 | Who can do what with a dispute | Use Case | The actors around the dispute process and what each may initiate. | 1.0 | Saadaoui Abdessalem | 2026-02-10 | BR-001, BR-003 | @startuml left to right direction skinparam packageStyle rectangle actor "Cardholder" as CH actor "Disputes agent" as AG actor "Card scheme" as CS rectangle "Card disputes" { usecase "Raise a dispute" as UC1 usecase "Attach evidence" as UC2 usecase "Investigate case" as UC3 usecase "Raise chargeback" as UC4 usecase "Notify cardholder" as UC5 } CH --> UC1 CH --> UC2 AG --> UC3 AG --> UC4 UC4 --> CS UC3 ..> UC5 : <<include>> @enduml
DGM-002 | Raising a dispute, end to end | Sequence | The calls made from the tap on Dispute to the provisional credit. | 1.1 | Saadaoui Abdessalem | 2026-02-12 | BR-001, BR-002 | @startuml autonumber actor Cardholder participant "Mobile app" as App participant "Disputes API" as API database "Disputes DB" as DB participant "Ledger" as Ledger Cardholder -> App : tap Dispute App -> API : POST /disputes API -> API : check status and 120-day window alt not eligible API --> App : 422 NOT_DISPUTABLE App --> Cardholder : reason shown else eligible API -> DB : insert dispute (Submitted) API --> App : 201 Created API -> Ledger : POST /postings (provisional credit) Ledger --> API : posted API -> DB : status = Under Review API --> Cardholder : notification end @enduml
DGM-003 | The life of a dispute | State | Every status a dispute may hold and the moves allowed between them. | 1.0 | Saadaoui Abdessalem | 2026-02-12 | BR-001, BR-004 | @startuml [*] --> Submitted Submitted --> UnderReview : accepted Submitted --> Rejected : ineligible UnderReview --> Resolved : in favour of cardholder UnderReview --> Rejected : evidence insufficient Rejected --> [*] Resolved --> [*] note right of UnderReview Provisional credit is in place from here end note @enduml
DGM-004 | Dispute data model | ER | The tables the dispute writes and the keys that join them. | 1.0 | Saadaoui Abdessalem | 2026-02-13 | BR-001, BR-002 | @startuml entity "card_transaction" as T { * transaction_id : uuid -- card_id : uuid amount : numeric(15,2) settled_date : date status : varchar(20) } entity "dispute" as D { * dispute_id : uuid -- transaction_id : uuid <<FK>> reason_code : varchar(10) amount : numeric(15,2) status : varchar(20) raised_at : timestamp } entity "dispute_evidence" as E { * evidence_id : uuid -- dispute_id : uuid <<FK>> file_name : varchar(255) size_bytes : bigint } T ¦¦--o{ D D ¦¦--o{ E @enduml
DGM-005 | Dispute process, BPMN | BPMN | The same flow in BPMN notation, with the lanes that own each step. | 1.0 | Saadaoui Abdessalem | 2026-02-14 | BR-001, BR-002 | @startuml !theme plain title Raise and settle a card dispute ¦Cardholder¦ start :Select a settled transaction; :Choose a reason code; ¦Disputes service¦ if (Eligible?) then (no) :Refuse and explain; stop else (yes) :Create dispute (Submitted); endif ¦Ledger¦ :Post provisional credit; ¦Disputes agent¦ :Investigate the evidence; if (In favour of cardholder?) then (yes) :Raise chargeback; ¦Disputes service¦ :Close as Resolved; else (no) ¦Ledger¦ :Reverse the credit; ¦Disputes service¦ :Close as Rejected; endif stop @enduml

## Wireframes
ID | Title | Screen ID | Description | Channel | Version | Status | Author | Last Updated | Annotations | Requirements
WF-001 | Transaction detail with the Dispute action | SCR-TXN-01 | Where the cardholder starts, and where the 120-day rule becomes visible. | Mobile | 1.1 | Approved | Saadaoui Abdessalem | 2026-02-11 | Dispute button is disabled past 120 days; the reason is shown beneath it, never as a toast | BR-001
WF-002 | Reason code selection | SCR-DSP-01 | A short list of reasons in the cardholder's words, not the scheme's. | Mobile | 1.0 | In Review | Saadaoui Abdessalem | 2026-02-13 | Each reason carries one line of plain explanation; no scheme codes on screen | BR-001
WF-003 | Open dispute with evidence | SCR-DSP-02 | Case status, the provisional credit, and the attach action. | Mobile | 0.3 | Draft | Saadaoui Abdessalem | 2026-02-18 | Attach is hidden once five files exist, rather than shown failing | BR-003, BR-004

## API Endpoints
Service | Base Path | ID | Method | Path | Summary | Description | Tag | Operation Id | Auth | Requirements
Disputes API | /disputes/v1 | API-001 | POST | /disputes | Raise a dispute against a settled transaction | Checks eligibility, creates the case and returns its reference. | Disputes | createDispute | OAuth2, scope disputes.write | BR-001
Disputes API | /disputes/v1 | API-002 | GET | /disputes/{disputeId} | Read a dispute and its provisional credit | Returns the case, its status history and any posting made against it. | Disputes | getDispute | OAuth2, scope disputes.read | BR-002
Disputes API | /disputes/v1 | API-003 | POST | /disputes/{disputeId}/evidence | Attach an evidence file to an open dispute | Accepts up to five files of 10 MB while the case is Under Review. | Evidence | addEvidence | OAuth2, scope disputes.write | BR-003
Disputes API | /disputes/v1 | API-004 | GET | /disputes | List the disputes on a card | Paged, newest first, filtered by status. | Disputes | listDisputes | OAuth2, scope disputes.read | BR-001

## SQL Validations
ID | Title | Purpose | Database | SQL | Columns | Status | Last Run | Executed By | Notes | Requirements | Rules
SQL-001 | Disputes raised outside the 120-day window | Proves RULE-002 holds in the data, not only in the code. | cards | SELECT d.dispute_id, t.settled_date, d.raised_at::date - t.settled_date AS days_elapsed FROM dispute d JOIN card_transaction t ON t.transaction_id = d.transaction_id WHERE d.raised_at::date - t.settled_date > 120 ORDER BY days_elapsed DESC; | dispute_id, settled_date, days_elapsed | Validated | 2026-02-20 | Saadaoui Abdessalem | Returns no rows; the window is enforced at creation | BR-001 | RULE-002
SQL-002 | Provisional credits that do not match the disputed amount | Proves RULE-003: the credit never exceeds what was disputed. | cards | SELECT d.dispute_id, d.amount AS disputed, p.amount AS credited FROM dispute d JOIN posting p ON p.dispute_id = d.dispute_id WHERE p.type = 'PROVISIONAL_CREDIT' AND p.amount <> d.amount; | dispute_id, disputed, credited | Validated | 2026-02-20 | Saadaoui Abdessalem | Returns no rows | BR-002 | RULE-003
SQL-003 | Disputes with more than five evidence files | Checks the attachment limit in RULE-004. | cards | SELECT dispute_id, COUNT(*) AS files FROM dispute_evidence GROUP BY dispute_id HAVING COUNT(*) > 5; | dispute_id, files | Needs Review | 2026-02-20 | Saadaoui Abdessalem | Rule not yet live; run again after the March release | BR-003 | RULE-004

## Test Cases
ID | Scenario | Suite | Preconditions | Steps | Expected Result | Status | Priority | Type | Requirement | Last Run | Executed By | Defect
TC-001 | A settled transaction inside the window can be disputed | Disputes | A card with a settled transaction dated 30 days ago | 1. Open the transaction -> the Dispute action is available 2. Choose a reason and confirm -> a reference is shown | The dispute exists with the status Submitted. | Passed | Critical | Functional | BR-001 | 2026-02-19 | Saadaoui Abdessalem
TC-002 | A transaction older than 120 days cannot be disputed | Disputes | A card with a settled transaction dated 130 days ago | 1. Open the transaction -> the Dispute action is disabled and the reason is shown | No dispute is created and the cardholder is told why. | Passed | Critical | Negative | BR-001 | 2026-02-19 | Saadaoui Abdessalem
TC-003 | A provisional credit is posted for the disputed amount | Settlement | A dispute of 84.50 accepted before the end-of-day run | 1. Run end of day -> a posting appears 2. Read the posting -> the amount is 84.50 | One provisional credit of 84.50 and no second posting. | Passed | Critical | Integration | BR-002 | 2026-02-20 | Saadaoui Abdessalem
TC-004 | The sixth evidence file is refused | Evidence | A dispute Under Review with five files attached | 1. Attach a sixth file -> the error ATTACHMENT_LIMIT is shown | The file is refused and the five existing files are untouched. | Failed | Medium | Negative | BR-003 | 2026-02-20 | Saadaoui Abdessalem | DEF-118
TC-005 | One notification per status change | Notifications | A dispute with the status Submitted | 1. Move it to Under Review -> one notification is sent | Exactly one notification, not one per retry. | Not Run | Medium | Functional | BR-004

## Documents
ID | Name | Format | Description | Category | Version | Author | Last Updated | Size | Status | Confidentiality | Requirements
DOC-001 | Card disputes — business requirements | Word | The signed requirements pack behind BR-001 and BR-002. | Requirements | 1.2 | Saadaoui Abdessalem | 2026-02-10 | 412 KB | Approved | Internal | BR-001, BR-002
DOC-002 | Disputes API contract | Swagger | OpenAPI 3.1 definition of the four dispute endpoints. | Interface | 1.0.0 | Saadaoui Abdessalem | 2026-02-15 | 38 KB | In Review | Internal | BR-001, BR-003
DOC-003 | Dispute process model | BPMN | The BPMN 2.0 file behind the process flow. | Process | 1.0 | Saadaoui Abdessalem | 2026-02-14 | 24 KB | Approved | Internal | BR-001